## Guidance Notes
Change Plan
Why Complete a High Level Change Plan for BP2?
Having completed your stakeholder analysis to identify those impacted by the change and your Change Impact Analysis to identify key activities, you're now ready to build out your Change Plan
The Change Plan will help identify key steps to achieve the required outcome to the deadline required by breaking down activities and allocating delivery dates
The template can be used to include activities where multiple solutions are being adopted by creating new worksheets for each solution
The Change Plan can be as detailed as you wish as long as it captures the key activities to embark, plan for, go live with and embeds the change
Some firms may prefer to use other project software tools such as MS Project and the key elements from this template can be added to those tools
Guidance for use:
Having decided on your BP2 pathway, consider your change plan for each solution (MRCv3, Transitional Services, IPOS, ICOS etc) and build out the plan by adding key activities and timelines
The 'Deciding to Adopt' section outlines early stage activities required ahead of adoption including building knowledge, applying it to you business to understand the impact and obtaining approval to move forward
The 'Plan for Adoption' section enables you to add activities under people, process and technology that need to be considered and completed ahead of adoption. This can be built out to be your 'business readiness plan'
The 'Go Live with Adoption' section helps you consider the activities required to go live including setting up users on new systems, training, Go / No Go decision, success metrics and tracking, and gathering feedback
The 'Roll Out and Embed' section is designed to ensure the focus continues beyond go live with key activities that need to be completed until the change can be classifies as moving to Business as Usual
Align change tasks with the project plan, if a project management approach will be used to roll out the technology. Work closely with the PM to execute the change tasks at the appropriate time during the initiative

## Change Plan
Change Plan
Prepare a plan per solution being adopted Change timescales and add tasks as required. Change the Start Date under week 1 in cell I13 | [72 empty] | RAG key: |  |  |  |  | On track
At risk
[7 empty] | PLEASE NOTE: All dates shown are provided as an example only. Please update with real dates for the change | [70 empty] | Will not be met
ACTIVITY | START | No of weeks | Milestone | Owner | Status | Notes | WEEKS | [70 empty] | Tools and guides
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71
 | time axis 2023-02-06 to 2024-06-10
DECIDE TO ADOPT | 1 | 6 | M | Name | Green
Understand solution and benefits to firm | 1 | 4 |  | Name | Amber | [72 empty] | Playbook and Benefits Framework
Identify key stakeholders using Stakeholder Analysis Tool | 1 | 4 |  | Name | Red | [72 empty] | Stakeholder Analysis Tool
Understand high level impact to firm and stakeholders | 2 | 3 |  | Name | Blue | [72 empty] | Change Impact Analysis Tool
Develop case for change prepared | 3 | 3 |  | Name | [73 empty] | Benefits Framework
Obtain internal approval to proceed | 5 | 2 |  | Name
PLAN ADOPTION | 7 | 9 | M | Name
Understand impact on people and processes | 7 | 8 |  | Name | [73 empty] | Change Impact Analysis Tool
Understand impact on technology | 7 | 8 |  | Name | [73 empty] | Change Impact Analysis Tool
Plan business readiness | 7 | 6 |  | Name
Plan Key Success Measures | 21 | 4 |  | Name
Plan Post Live Feedback Processes | 21 | 4 |  | Name
Plan IT readiness | 8 | 6 |  | Name | [73 empty] | Change Impact Analysis Tool
Add rows for activities identfied in your stakeholder and impacts analysis | 7 | 9 |  | Name
Deliver communications | 8 | 9 |  | Name
Prepare leaders and their people for the change | 10 | 45 |  | Name
Design and approved roll out plan | 10 | 45 |  | Name
Identify users and gain systems access | 10 | 5 |  | Name | [73 empty] | Change Impact Analysis Tool
Update and issue process guides | 17 | 6 |  | Name
Train users | 14 | 17 |  | Name | [73 empty] | Change Impact Analysis Tool & Training Materials
Participate in Market Acceptance Testing | 58 | 6 |  | Name
GO LIVE WITH THE CHANGE | 71 | 4 | M | Name
Go / No Go meeting held and decsion communicated | 71 | 1 |  | Name
Communicate through go live | 71 | 2 |  | Name
Check initial transactions work as expected | 71 | 2 |  | Name
Start tracking Key Success Measures | 71 | 12 |  | Name
Check in with users and get feedback | 71 | 1 |  | Name
Report, resolve or escalate issues | 71 | 4 |  | Name
Track key performance indicators | 71 | 12 |  | Name
ROLL OUT AND EMBED | 71 | 12 | M | Name
Track progress against roll out plan | 71 | 12 |  | Name
Learn lessons from initial roll out as new teams come on board | 71 | 12 |  | Name
Check in and ensure the new way of working becomes the new BAU | 71 | 12 |  | Name
Note on B6: The key activities included in the template plan are to help you plan for successful adoption. We consider these to be the most important steps. If any are not applicable delete the row. If there are additional key activities simply add rows.
Note on C6: This is the start week from row 8. e.g. 12 is week commencing 12/04/23 and will update the bar to right the date cells
Note on D6: Add the number of weeks allocated to each activity and will update the bar to right the date cells
Note on E6: Enter M if the activity refers to a milestone. This then generates a box around the final week of the task as a visual representation of the milestones. The defaults are the end of each high level stage. However, use the template in the way that works for you and your organisation.
Note on F6: Enter the name of the person responsible for the task.
Note on G6: To keep the plan live, update the status of the key activities. The statuses are: Blue - Activity is complete Green - Activity is on track for completion on time Amber - Issues mean that the activity or delivery date is at risk Red - Issues mean that the activity date will not be met and remedial action is required
Note on H6: Use for explanatory notes relating to the activity or progress.
Note on B22: It is highly likely that you will add some additional activities depending on the nature of the change - for example, testing.
Note on CC6: Author: The sources noted may be of assistance for these activities